## Overview
To-Do List
TASK | PRIORITY | ESTIMATE(Day) | STATUS | START DATE | DUE DATE | % COMPLETE | DONE? | NOTES
Monitor Process | High | 5 | In Progress |  | 2016-11-10 | 0% | 0
[6 empty] | 100% | 1
[6 empty] | 100% | 1
[6 empty] | 100% | 1
[6 empty] | 0% | 0
0
0

## SyncImageClient (hidden)
SyncImageClient
TASK | PRIORITY | STATUS | START DATE | DUE DATE | % COMPLETE | DONE? | NOTES
UploadLaneInImage | High | Complete | 2016-10-28 | 2016-11-09 | 100% | 1 | Done
UploadLaneOutImage | High | Complete | 2016-10-28 | 2016-11-09 | 100% | 1 | Done
DownloadLaneInImage | High | Complete | 2016-10-28 | 2016-11-09 | 100% | 1 | Done
SyncProcess | High | Complete | 2016-10-28 | 2016-11-09 | 100% | 1 | Improving
Optimize Sync Time | Normal | In Progress | 2016-11-10 | 2016-11-25 | 75% | 0 | Improving
0
0

## Monitor Process
Monitor Process
TASK | PRIORITY | ESTIMATE(Hour) | STATUS | START DATE | DUE DATE | OWNER | % COMPLETE | DONE? | NOTES
Desktop
Giao diện | Normal | 0 | Complete | 10/04/2017 | 11/04/2017 | Thang, Ron | 100%
AccessDatabase | Normal | 0 | In Progress | 10/04/2017 | 12/04/2017 | Phong | 0% | 0
Create Database(table,store) | Normal | 0 | Complete | 10/04/2017 | 10/04/2017 | Cả team | 100% | 1
Show dữ liệu lên giao diện | Normal | 0 | In Progress | 10/04/2017 | 14/04/2017 | Nhan | 0%
Show cảnh báo | Normal | 0 | In Progress | 10/04/2017 | 14/04/2017 | Viet | 0% |  | So sánh với dữ liệu trong DB để thông báo
Web
Giao diện | Normal | 0 | Complete | 10/04/2017 | 14/04/2017 | Thien | 100% | 1
AccessDatabase | Normal | 0 | In Progress | 10/04/2017 | 12/04/2017 | V.Truong | 0%
Show dữ liệu lên giao diện | Normal | 0 | In Progress | 10/04/2017 | 14/04/2017 | Huy | 0%
Show cảnh báo | Normal | 0 | In Progress | 10/04/2017 | 14/04/2017 | Huong | 0% |  | So sánh với dữ liệu trong DB để thông báo